## Cover Page
The VibeCoders
Prepared By:
Sonia Singh
Eduardo Bermudez
Xanthippe Pentovelis
Hoai Kiet Tran
Omar Eshatti

## Product backlog planning
Issue # | User Story Title | Task Description | Story Points (1,2,3,4,5) | Due Date | Priority | Risk | Assignmed Members | Sprint
#1 | Story 1: A user should be able to register an account | - Create a homepage interface - Create a registration page - Implement backend logic to handle password and username storing - Implement success and error page | 5 | February 6 2026 | High - user cannot access the app without | Medium-High - involves security concerns | Sonia | #1
#2 | Story 2: A user should be able to login into an account | - Create login page - Implement backend logic to handle password and username verification - Create authentication session - Implement frontend to store token/session | 5 | February 6 2026 | High - necessary for authenticated features access | Medium - can introduce bugs that prevent access | Eduardo | #1
#3 | Story 3: A user should be able to logout from an account | - Create a logout button in the homepage interface - Implement frontend to clear token/session | 3 | February 6 2026 | Medium - important but does not prevent usage | Low - minimal technical complexity | Omar | #1
#4 | Story 4: A user should be able to access protected pages only after authentication | - Define which routes/pages are protected - Add authentication guard - Backend middleware to protect API routes | 3 | February 6 2026 | High - necessary to prevent unauthorized access | Medium - can expose private data | Eduardo | #1
#5 | Story 5: A user should be able to view their profile | - Create profile page UI - Implement frontend to fetch and display profile data | 3 | February 6 2026 | High - core feature | Medium - need to avoid data leakage | Xanthippe | #1
#6 | Story 6: A user should be able to edit their profile | - Create editable fields on profile page (diet+allergies) -Implement backend logic to store diet and allergies | 3 | February 6 2026 | High - Core feature | Medium | Tran | #1
#7 | Story 7: A user should be able to enter a new recipe by entering its details | -Create a recipe interface -Add input fields -Implement client side validation - Implement backend logic to handle recipe storing | 3 | February 27 2026 | High- Core feature | Medium | Sonia | #2
#8 | Story 8: A user should be able to edit an existing recipe | - Create "edit recipe" ui -Fetch recipe details by ID -Create fields to edit ingredients, time , steps cost -Implement backend logic to handle recipe updates and storing | 5 | February 27 2026 | Medium - important but does not prevent usage | Medium | Eduardo | #2
#9 | Story 9: A user should be able to filter recipes by attributes | - Normalize ingredient structure - Define recipe schema/model -Implement backend logic for attribute storing | 3 | February 27 2026 | Medium - important but does not prevent usage | Medium | Tran | #2
#10 | Story 10: A user should be able to delete a recipe | - Create a delete button in the recipe interface -Implement backend logic to handle recipe deletion and storing | 4 | February 27 2026 | High- Core feature | Medium | Omar | #2
#11 | Story 11: A user should be able to access a modern and intuitive interface | - Make the website have a consistent scheme and typography - Make the buttons and interactive elements visually consistent - Make the pages load without visual glitches | 4 | February 27 2026 | High - Core feature | Medium | Xanthippe | #2

## Sprint1
1.1 | Create registration page UI (form + basic styling) | Design and implement the user interface for the registration page. The page should contain a form where new users can enter their email and password to create an account. The layout should be simple and consistent with the rest of the application. | Story point: 3 | Priority:High | Risk:Low-Medium
1.2 | Client-side validation (email format, password rules) | Implement client-side validation for the user registration form. The system should validate user input before submitting the form to the backend to ensure basic requirements are met. | Story point: 2 | Priority: High | Risk:Low
1.3 | Backend endpoint: POST /auth/register | Create a backend API endpoint that allows new users to register. The endpoint should accept user credentials from the frontend, validate the input, and create a new user in the database. | Story point: 5 | Priority: High | Risk:Medium
1.4 | Hash passwords + store user in DB | Implement secure password handling when creating new user accounts. User passwords must be hashed before being stored in the database to ensure security. The hashed password and user information should then be saved in the database. | Story point: 3 | Priority: High | Risk: Low-Medium
1.5 | Handle errors (duplicate email, invalid input) | Implement proper error handling for the user registration process. The system should detect and respond to common error cases such as missing fields, invalid input, and duplicate email addresses. Clear and user-friendly error messages should be returned to the frontend. | Story point: 2 | Priority: High | Risk: Low
1.6 | Success flow (redirect + success message) | Implement the success flow after a user successfully registers. The user should receive a confirmation message and be redirected to the appropriate page (such as the login page or dashboard). This ensures a smooth and clear user experience. | Story point: 2 | Priority: Medium | Risk: Low
2.1 | Create Login Page UI | Design and implement the user interface for the login page. The page should contain a form where existing users can enter their email and password to log in. The layout should be simple and consistent with the rest of the application. | Story point: 2 | Priority: High | Risk: Low
2.2 | Backend endpoint: POST /auth/login | Implement a backend endpoint that authenticates users using their email and password. | Story point: 2 | Priority: High | Risk: Medium
2.3 | Verify password (compare hash) | Verify the user’s password by comparing the submitted password with the hashed password stored in the database. | Story point: 1 | Priority: High | Risk: Low
2.4 | Create auth session (JWT or cookie session) | Create an authentication session for the user after successful login. | Story point: 2 | Priority: High | Risk: Medium
2.5 | Store token / session on frontend | Store the authentication token or session on the frontend to maintain login state. | Story point: 1 | Priority: High | Risk: Low
2.6 | Redirect after login | Redirect the user to a protected page after successful login. | Story point: 1 | Priority: Medium | Risk: Low
2.7 | Invalid credentials show error message | Display a user-friendly error message when login fails due to invalid credentials. | Story point: 1 | Priority: High | Risk: Low
2.8 | Quick test: login works end-to-end | Perform a quick end-to-end test to verify that the login flow works correctly. | Story point: 1 | Priority: Medium | Risk: Low
3.1 | Add Logout Button | Add a logout button to the interface so authenticated users can log out. | Story point: 1 | Priority: Medium | Risk: Low
3.2 | Clear Authentication State | Clear frontend authentication state when the user logs out. | Story point: 1 | Priority: Medium | Risk: Low
3.3 | Redirect After Logout | Redirect the user after logout and prevent access to protected pages. | Story point: 1 | Priority: Medium | Risk: Low-medium
3.4 | Logout Verification | Verify that the logout functionality works correctly and that protected pages are inaccessible after logout. | Story point: 1 | Priority: Medium | Risk:Low
4.1 | Define protected routes/pages | Define which frontend pages and backend routes require authentication so only logged-in users can access account features. | Story point: 1 | Priority: High | Risk: Low
4.2 | Add auth guard (frontend route protection) | Add frontend route protection so users who are not logged in are redirected to the login page when accessing protected pages. | Story point: 2 | Priority:High | Risk: Medium
4.3 | Backend middleware to protect API routes | Protect backend API routes by rejecting requests that are not authenticated. | Story point: 2 | Priority: High | Risk: Medium
4.4 | Persist auth state (read token/cookie on app load) | Persist authentication state so that refreshing the page does not log the user out (depending on token/cookie strategy). | Story point: 2 | Priority: High | Risk: Medium
4.5 | Quick test: refresh keeps user logged in | Perform a quick end-to-end test to confirm protected routes work and authentication persists on refresh. | Story point: 1 | Priority: Medium | Risk:Low
5.1 | Create profile page UI | Build a responsive profile page that displays the user’s account information, including loading and error states, following the app’s design system. | Story point: 3 | Priority:Medium | Risk:Low
5.2 | Backend endpoint: GET /users/me | Implement an authenticated API endpoint that returns the currently logged-in user’s profile data while excluding sensitive fields. | Story point: 3 | Priority: High | Risk: Medium
5.3 | Connect frontend to fetch and display profile data | Fetch the authenticated user’s profile data from the backend and display it on the profile page with proper loading and error handling. | Story point: 2 | Priority: High | Risk: Low
5.4 | Ensure auth required (only logged-in users) | Restrict access to the profile page so only authenticated users can view it, redirecting unauthenticated users to the login page. | Story point: 2 | Priority:High | Risk: Medium
5.5 | Quick test: correct user data displays | Verify that the profile page shows the correct data for the logged-in user and prevents access to other users’ information. | Story point: 1 | Priority: Medium | Risk: Low
6.1 | Profile Page UI - Diet & Allergy Fields | Implement the frontend user interface elements that allow a user to view and edit their specific dietary requirements and allergy list. | Story point: 2 | Priority: Medium | Risk: Low
6.2 | Backend API - Update User Preferences | Create the server-side logic to handle incoming update requests for a user's dietary and allergy profiles. | Story point: 3 | Priority: High | Risk: Medium
6.3 | Data Validation & User Feedback | Implement safeguards to ensure data integrity and provide visual confirmation to the user that their changes were successful. | Story point: 2 | Priority: Medium | Risk: Low
6.4 | Database Persistence for User Preferences | Ensure that all dietary preferences and allergy updates submitted by the user are correctly mapped and stored in the database to allow for long-term persistence. | Story point: 2 | Priority: High | Risk: Medium
6.5 | User Feedback & Confirmation UI | Provide the user with immediate visual confirmation after they attempt to save their profile changes to improve the user experience. | Story point: 1 | Priority: Low | Risk: Low
6.6 | Persistence & Refresh Testing | Conduct a final verification to ensure that the integration between the frontend and backend is seamless and that data is being fetched correctly upon page load. | Story point: 1 | Priority: Medium | Risk: Low

## Sprint 2
7.1 | Design "Create Recipe" UI form | Design and implement the frontend UI for the “Create Recipe” page where users can enter all required recipe information. This task focuses only on the structure and layout of the form, ensuring all necessary fields are present and usable. Styling should remain simple and consistent with the rest of the application. | Story point: 3 | Priority: High | Risk: Low
7.2 | Implement Recipe Form Input Fields | Implement all required input fields inside the “Create Recipe” form. This task focuses on adding structured and functional form fields so users can enter complete recipe information. Dynamic ingredient fields should allow users to add or remove multiple ingredients. | Story point: 5 | Priority: High | Risk: Medium
7.3 | Add Client-Side Validaiton for Create Recipe Form | Add client-side validation to the “Create Recipe” form to ensure users provide all required information and enter valid numeric values before submitting. This improves user experience by catching errors early and displaying clear feedback messages. | Story point: 3 | Priority: High | Risk: Low
7.4 | Create POST /recipes Endpoint | Create a backend API endpoint that allows the frontend to submit a new recipe to the server. This task focuses on setting up the Express route/controller to receive recipe data in the request body and return proper responses (without implementing database saving yet). | Story point: 3 | Priority: High | Risk: Medium
7.5 | Validate Recipe Data (POST /recipes) | Implement backend-side validation for incoming recipe data sent to POST /recipes. This ensures the server rejects incomplete or invalid recipes even if client-side validation is bypassed. Validation should check required fields, correct types, and valid numeric values before allowing the request to proceed further. | Story point: 3 | Priority: High | Risk: Medium
7.6 | Save recipe to database | Implement the database persistence layer for recipe creation. After backend validation passes, the server should create a new recipe document/record and save it in the database (MongoDB). The endpoint should return the saved recipe (or its ID) and handle database-related errors properly. | Story point: 3 | Priority: High | Risk: Medium
7.7 | Handle success and error responses | Implement complete success and error handling for the Create Recipe flow. The backend must return consistent HTTP status codes and response bodies, and the frontend must interpret those responses to show a success message or redirect on success, and show helpful error messages on failure. | Story point: 3 | Priority: High | Risk: Medium
8.1 | Create Edit Recipe UI & Pre-fill Data | Create an “Edit Recipe” view that fetches an existing recipe by ID and pre-fills the form with current data. | Story point: 2 | Priority: High | Risk: Low
8.2 | Enable Editing & Update | Allow users to edit recipe fields and persist changes through a backend update endpoint. | Story point: 3 | Priority: High | Risk: Medium
9.1 | Define recipe schema/model | As a developer, I want to define the recipe schema/model so that all recipe data follows a consistent structure. | Story point: 2 | Priority: Medium | Risk: Medium
9.2 | Normalize ingredient structure | As a developer, I want to normalize the ingredient structure so that ingredient data is consistent and queryable. | Story point: 2 | Priority: Medium | Risk: Low
9.3 | Ensure database supports arrays/lists | As a developer, I want to ensure the database supports arrays/lists so that recipes can store multiple ingredients and steps. | Story point: 2 | Priority: Medium | Risk: Medium
9.4 | Validate schema consistency across frontend and backend | As a developer, I want to validate schema consistency across frontend and backend so that data integrity is maintained throughout the application. | Story point: 2 | Priority: Medium | Risk: Medium
10.1 | Add Delete Button & Confirmation UI | Add a delete button to each recipe view and implement a confirmation dialog to prevent accidental deletions. | Story point: 2 | Priority: Medium | Risk: Medium
10.2 | Implement DELETE Backend Endpoint | Create backend endpoint to remove recipe from database and return proper responses. | Story point: 3 | Priority: High | Risk: Medium
10.3 | Update Frontend After Deletion | Update UI immediately after recipe deletion without requiring page refresh. | Story point: 2 | Priority: Medium | Risk: Low
10.4 | Handle Errors & Validation | Handle backend and frontend errors during deletion process. | Story point: 2 | Priority: Medium | Risk: Medium
11.1 | Redesign Visual Style (Colors, Typography, Components) | Update the overall visual design of the website by improving the color scheme, typography, and reusable UI components (buttons, forms, cards). Ensure consistency across all pages. | Story point: 2 | Priority: Medium | Risk: Medium
11.2 | Improve Layout & Nagivation Usability | Enhance page structure and simplify navigation to improve readability and user flow. | Story point: 2 | Priority: High | Risk: Medium
11.3 | Optimize Responsiveness & Frontend Cleanup | Refactor frontend styles to improve responsiveness, maintainability, and cross-browser compatibility. | Story point: 1 | Priority: Medium | Risk: Low