## Cover Page
The VibeCoders
Prepared By:
Sonia Singh
Eduardo Bermudez
Xanthippe Pentovelis
Hoai Kiet Tran
Omar Eshatti

## Product backlog planning
Issue # | User Story Title | Task Description | Story Points (1,2,3,4,5) | Due Date | Priority | Risk | Assignmed Members
#1 | Story 1: A user should be able to register an account | - Create a homepage interface - Create a registration page - Implement backend logic to handle password and username storing - Implement success and error page | 5 |  | High | Medium-High
#2 | Story 2: A user should be able to login into an account | - Create login page - Implement backend logic to handle password and username verification - Create authentication session - Implement frontend to store token/session | 5 |  | High | Medium
#3 | Story 3: A user should be able to logout from an account | - Create a logout button in the homepage interface - Implement frontend to clear token/session | 3 |  | ? | ?
#4 | Story 4: A user should be able to access protected pages only after authentication | - Define which routes/pages are protected - Add authentication guard - Backend middleware to protect API routes | 3 |  | High | Medium
#5 | Story 5: A user should be able to view their profile | - Create profile page UI - Implement frontend to fetch and display profile data | 5 |  | High | Medium
#6 | Story 6: A user should be able to edit their profile | - Create editable fields on profile page (diet+allergies) -Implement backend logic to store diet and allergies | 3 |  | Medium | Low